## OS
WORKING GROUPS MONTHLY ACTIONS |  |  | Oct | Nov Meeting
Part complete
WORKING GROUP: |  | OPEN SPACES |  | Complete
TEAM: |  | E.Bell, A. Marr, S Rimmington, D. Parris |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Recreation Ground - Play and sports equipment, Concrete roundels,
Area behind Medway Inn, CCTV area |  |  | Naval Green - Maintenance of Furniture.
Wouldham Common - Fly Tipping, Litter Picking |  |  | Village Green - Maintenance of Furniture.
Grass Cutting - Ensure contract is adhered to. |  |  | Allotments - Liaise with Allotment Association
Develop and progress any special projects identified in the precept
To develop, support and monitor Risk Assessments in liaison with H&S
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS/ COMPLETE/RESULT
Lease for G West | TM | Draft lease written | PC to agree | Meet with Mr West to sign lease and agree works. He also needs to re-site roundel again.
Wouldham Common |  | Signage ordered | Signs ready for collection | put up
New play equipment | EB/TM | 3 quotes obtained | Item ordered | Chase delivery and installation
grass cutting areas | EB | Contract update | Instruction given for one complete round of works. Invoice due to see if additional works can be added. | monitor
Vandalised benches | EB | how much can be spent | Agreed to put on hold until works on the park have been completed. SB to find out prices of metal benches similar to those on the esplanade | On Hold
Gate at area behind church | DP | Clerk contacted Savilles who look after the site for Tarmac | Clerk chased progress | Savilles have completed repair. No futher action
Naval Estate | DP | Bench etc okay | Clerk has spoken to owner of bench. He has arranged for it to be sanded and revarnished | TMBC have confirmed they have taken responsibility of the bench and will schedule it for refurbishment.
Naval Estate | DP | Dangerous trees | Tree and suckers removed | Complete
Signage on Rec | DP | AB and SR to re-site car park rules sign | 3 'rules' signs received | Needs installation with No Horses sign
Free Trees | EB | To acquire free trees from KCC | Awaiting review
Cuxton FC using the Rec | TM | Enquiry from Cuxton FC to use the Rec | Awaiting response from FC meeting
Fly tipping Scarborough Lane | EB | Reported dumped mattresses | Report number 176481
Bushes along Meadow Way need clearing | SR/TM | The area along Meadow Way has not been cleared by the contractor | SB and TM cleared the site leaving a couple of bushes. It will need to be done again shortly to ensure brambles are kept under control
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## RFL
WORKING GROUPS MONTHLY ACTIONS |  |  | Oct | Nov Meeting
Part complete
WORKING GROUP: |  | ROADS, FOOTPATHS & LIGHTING |  | Complete
TEAM: |  | A. Marr, S. Buchanan, M. Savaryn, A McDermott |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Notify relevant authorities/companies of potholes, damaged road furniture, fly tipping, and signage.
Monitor overgrown vegetation, safe pavement surfaces and report as necessary.
Report lights not working - electric equipment, any lights that have vegetation on them either causing safety issues or blocking out the light.
Village Car Park and pathway |  | monitor condition and signage
Special Projects: | develop and progress any special projects identified in the precept
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS COMPLETE/RESULT
light in Ferry Lane | SB | Shield fitted but not working | Email sent to contactor to come back. SB informed resident | Awaiting response.
lights in Oldfield Drive | EB | identified problem will be solved | Now seem to be working correctly
car park lights | EB | Passed to RFL to research
Recreation Pathway Lights | EB | RFL to reseach solar bollards
White lines along Hall Road | SB/ TM | Clerk spoken to KCC | They will not refresh until coverage is <50% | KCC will look at doing it in the Spring
Reflectors on bollards | TM | To put additional reflective tape on bollards in Hall Road | Red and white tape put each side of bollards in Hall Road and Knowle Road. | Reported to KCC that the bollard in Knowle road had a white reflector where it should be red
Dropped gully on High Street | TM | Reported to KCC | Spoke to KCC who are looking at all the dropped gullys on the High Street. Will need to do a road closure. | Due to be carried out 26/10
Water leak 55 High Street | DP | Reported to KCC | Asked KCC to do at the same time as the gullies.
One Way Trial |  | New options given by KCC to drop scheme, change it or continue and risk buses not running | Meeting arranged with KCC,BPC and WPC for 1/11
Light in Scarborough Lane | TM | Burham PC want to take this off their inventory | Need to arrange for fuse to be removed. But need to confirm with BPC which light.
White lines in car park | EB/TM | TM met with potential contractor to quote for re-lining outside of carpark | This will give an additional 8 spaces to giving 30 spaces for residents only.
Blocked drain and flooding around Trafalgar/Nelson |  | Reported to KCC Ref: 660406 | Advised by KCC that the Southern Water system is not sufficient for heavy rain | Continue to monitor and report
pothole outside 177 | EB | KCC ref 661833 | 14 days max
loose cable 180 | EB | openreach ndoexe02
Resident Complaint about parking on grass verge in Nelson | TM | Research ownership and report to KCC
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## VH
WORKING GROUPS MONTHLY ACTIONS |  |  | MONTH ___Oct | Nov Meeting
Part complete
WORKING GROUP: |  | VILLAGE HALL |  | Complete
TEAM: |  | A. Marr, S. Buchanan, D. Parris |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To plan for the ongoing development with the VH Charity, making recommendations as appropriate
Oversee and agree the terms and conditions of use of the facilities
Oversee and agree the fees relating to the hire of the facilities
Ensure that regular risk assessments and health and safety checks are made in line with current legislation
Ensure the provision of safe and well-maintained facilities for the community use.
Ensure Governing/Deed of Trust document is adhered to
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
Tidy front garden of Village Hall | EB | Grass Cut | Possible 5th August | Complete/ongoing
Governance/Transfer | TM | Sent requests for quotations to specialist solicitors | Chased quotation from Furley Page
Rear Fire exit blocked | TM | Letters written to residents. No feedback received | Only 1 fire exit is legaly required for building. Evacuation plan to be updated | Evacuation plan changed.
Major crack in toilet block (structural?) | TM | Claim reference 27220000430. | Claim accepted. Insurance sent contactor to produce a schedule of works 25/8 | Note there will be £1000 excess
Drainage | AM | AM has contacted a builder to dig a trench around the front of the Hall to allow better drainage | Trench has been dug and guttering cleaned and fixed. | complete
MacMillan Coffee Morning | AM | A fund raising Coffee Morning to be held | The date set is 7/10. Councillors are asked to attend if possible | Raised £61.10
Internal Painting | AM | Work parties attending w/c 24/10 | Colour scheme agreed with users and paint acquired
External Painting | AM | Local volunteer has agreed to paint the front of the Hall
Accessible toilet | AM | Potential contractors attended to quote for works | Full plans to be drawn up and discussion with TMBC planning need to take place
Trustee resignation | TM | Resignation has been received from T. Cranfield | Removed as Trustee from Charity | complete
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## H&S
WORKING GROUPS MONTHLY ACTIONS |  |  | September | Oct Meeting
WORKING GROUP: |  | H & S
TEAM: |  | S. Rimmington, D. Parris, A. McDermott
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
Monitor the Councils compliance with relevant legislation and progress towards best practice in health and safety including 1974 Health & Safety at Work Act
To ensure the Council’s Health and Safety Policy is implemented, monitored, developed, communicated effectively, reviewed and amended as required.
To ensure suitable and sufficient funds, people, materials and equipment are provided to meet all health and safety requirements
Ensure adequate insurance cover is provided and renewed
Ensure any accidents, ill health and 'near miss’s are recorded, investigated and reported where necessary
Ensure any safety issues raised are thoroughly investigated and, when necessary, further effective controls implemented
Ensure contractors engaged are reputable, can demonstrate a good health and safety records and are made aware of relevant local health and safety rules and procedures
To develop an emergency plan/disaster recovery plan involving other partners/officials where necessary and assigning a designated competent person in charge of the planning and control measures for situations involving imminent danger
Develop flood risk planning in conjunction with (h)
Develop, monitor and review risk assessments linking with the relevant committee.
Ensure checks of capital equipment and assets are made and any remedial actions taken
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS, COMPLETE/RESULT
Review H&S for the VH | TM | Started to compile a H & S File | Requested RA's from regular users | Received from Brownies
Remedial work on ROSPA rep | TM | Quotes sought for remedial work | Emergency works ordered | Need to chase for start date
Gate to play area in Rec not closing properly | TM | MS to look at re-aligning
Non closing gate at the top of the Rec | ? | Need to look at a 'soft' spring to enable self closing.
Fire Exits at the VH | TM | Electrician advised only one exit is needed for the size of the Hall even if others could be used in a emergency. | 1.Clerk to update evacuation plan to use the front door. 2.Clerk to check number of exits required for nurseries | 1. Done 2. Checked with Early Years. It only states Fire RA needs to be considered and exit identified and free from blockages
Emergency lights for VH | AM | Works arranged to update fire exit signs to meet current legislation. Emergency light to also be fitted to toilet block | Completed 25/10 | Once work is completed, ask Fire Brigade to visit
Defibrillator | TM | Defib at the Village Hall used by SECAM. Need to be checked. Investigations on where to put the spare one. | Contacted Church to find out costs and who will do it. | Look at donation for graveyard to cover costs of installing
Defibrillator Village Hall | TM | The unit has been used by SECAM | Check to see if pads have been used | Complete. Re-registered
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## Planning
WORKING GROUPS MONTHLY ACTIONS |  |  | Sept | Oct Meeting
WORKING GROUP: |  | PLANNING
TEAM: |  | E.Bell, A. Baker, A. McDermott, S. Buchanan
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To make representations to the Local Planning Authority on applications for planning permission which have been notified to the Council
To make representations in respect of appeals against the refusal of planning permission
To identify and make representations to the relevant authorities in respect of enforcement action or any matters considered to be breaches of planning regulations;
The Working Group will consider each application on its merits.
All Parish Council members are notified of applications within 3 working days of Parish meeting and may be viewed via the Tonbridge and Malling Planning Portal. All Committee decisions will be recorded in the Parish Council minutes.
The Working Group, whilst considering the views of residents and other interested parties, is not duty bound to pass on these views when making its decision, they may submit a budget to the Council as part of the Council’s overall budget process.
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/ RESULT
22/02052/FL Gardeners Cottage 29 Keepers Cottage Lane - Replace modern garage and workshop with a new 3 bedroom bungalow and demolition of Grade II listed, dilapidated modern kitchen on Gardeners Cottage |  | No Comment
22/01843/ LDEVillage Centre Parcel LC Peters Pit And Peters Works Site Hall Road - Lawful Development Certificate Existing: To confirm a material operation has been carried out at the Medical Centre at Peters Village under planning permission TM/19/01949/FL |  | This certificate was approved to say that works have started on the Medical Centre | No Comment
22/00836/FL 19 Laker Road Rochester - Construction of a rear extension at 19 Laker Road to expand the storage area of the warehouse |  | No Comment
Downs Farm Area 3 meeting | EB | EB has met with BCllrs and will present at the Area 3 meeting on 6/10 | Title registers purchased for the property and adjacent land | Deferred for site meeting to take place on 2/11
RESOLUTIONS TO FULL COUNCIL:

## F&A
WORKING GROUPS MONTHLY ACTIONS |  |  | August
WORKING GROUP: |  | FINANCE
TEAM: |  | E.Bell, A. Baker, S. Rimmington
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To consider the quarterly budget monitoring reports provided by the Clerk with any recommendations being put to the Council.
To consider the annual budget and the annual precept and take recommendations and comments to the full council.
All Council members will be provided with a list of payments for approval prior to each Council meeting. Any payment can be queried at the Council meetings. If necessary, a vote be taken to authorise payment with the Chairman of the Council Meeting having the casting vote when there are equal numbers of votes.
A member of the Committee will sign off the bank statement from the previous month, at each Council meeting.
During each Council meeting, 2 bank signatories, will agree payments for the month.
To monitor staffing in line with the Terms of Reference
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
date of quarterly meeting/ budget review | TM | Dates circulated | Held on 25/10
Liz Phillips's appraisal | TM | Appraisal form sent | Appraisal due 31/10
Pay review for precept | TM | Calculations circulated based on NALC increase | To be agreed at finance meeting
SR to be added to signatory list | TM | Raised mandate | awaiting sign off SR | paperwork sent out again
RBLI donation for Wreath | TM | Request placed | Chq to be raised and sent. | Done
Annual Investment Strategy needed as funds exceed 100k | TM | Write strategy for approval
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL: |  | To approve Annual Investment Strategy