## OS
WORKING GROUPS MONTHLY ACTIONS
Part complete
WORKING GROUP: |  | OPEN SPACES |  | Complete
LEAD |  | L. Church, |  | Outstanding
RESPONSIBILITIES: To meet, monitor and report on the following:
Recreation Ground - Play and sports equipment, Concrete roundels,
Area behind Medway Inn, CCTV area |  |  | Naval Green - Maintenance of Furniture.
Wouldham Common - Fly Tipping, Litter Picking |  |  | Village Green - Maintenance of Furniture.
Grass Cutting - Ensure contract is adhered to. |  |  | Allotments - Liaise with Allotment Association
Develop and progress any special projects identified in the precept
To develop, support and monitor Risk Assessments in liaison with H&S
ISSUE RAISED | LEAD | ACTION TAKEN | ONGOING ACTIONS | NEXT STEPS/ COMPLETE/RESULT
Wetpour damage | JM | Repaired large holes under climbing frame | Need to complete repair under slide and fill in gaps around equipment | Need to look at complete resurface in next budget
Wetpour damage | JM | Purchased gap filler and green wetpour | Due to be delivered w/c 30/6 | Arrange a day to fill gaps around equipment
Trip risk due to security bolts next to container | JM | Removed screws and placed in container |  | Can be re-installed once new picnic bench purchased
D Bolts on swings need replacing | LC | New bolts installed | Seats need to be raised. Awaiting adjusters to arrive | Raise seats by 300mm
Hedges at bungalows on Hall Lane | JM | Cut Back main hedge and cut bramble runners along Hall Road footpath | Clerk to check with Clarion to continue maintenanance | Clarion have fully cut back.
Area by sub station in carpark | JM | Fully weeded and put bark down | Need to add more plants and water regularly | Ongoing watering and weeding
Fence by sub station | TY/EB | Volunteer has re-used fence from the VH and installed to stop people walking over ground | Need to weed the area alongside the new fence | Completed. Ongoing maintenance
RESOLUTIONS TO FULL COUNCIL:

## RFL
WORKING GROUPS MONTHLY ACTIONS |  |  |  | May
Part complete
WORKING GROUP: |  | ROADS, FOOTPATHS & LIGHTING |  | Complete
LEAD |  | C.Collier Ward, |  | Outstanding
RESPONSIBILITIES: To meet, monitor and report on the following:
Notify relevant authorities/companies of potholes, damaged road furniture, fly tipping, and signage.
Monitor overgrown vegetation, safe pavement surfaces and report as necessary.
Report lights not working - electric equipment, any lights that have vegetation on them either causing safety issues or blocking out the light.
Village Car Park and pathway |  | monitor condition and signage
Special Projects: | develop and progress any special projects identified in the precept
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | NEXT STEPS COMPLETE/RESULT
Hedges and footpath alongside the allotments | JM | Strimmed footpath and cut back runner brambles. Checked fence- currently secure due to the bramble growth. | Checked hedges and cannot cut back during October due to birds nesting | Once hedges are cut, repair the barb wire fence.
Footpath from tin bridge to Pilgrims Way | TM | Instructed Contractor | Inspected: Still passable, but crops growing | Chase contractor
Footpath alongside the Rec | JM | Cut back running brambles and overhanging trees | Keep trimming whilst out walking | Look at having a 'contractor cut at the end of August
City Fibre late night working on Knowle Road | TM | Submitted formal complaint | TTRO was revoked with the assurance that future work would need to be done during the day. | Report any further work
Repairs to humps in Hall Road | KCC | Complete | Complaint to KCC as no signage had been put out prior to road closure | Another closure is due to complete the white line repaint
Knowle Road speed restriction to 20mph | KCC | With KCC Design dept | On agenda to be discussed at PC meeting on 1/7/25 | Report back to KCC
Pilgrims Way surface repairs | KCC | Initial agreemement for KCC to resurface and repair passing bays | Marked up, but no dates given | Keep pushing and make sure they repair curbs at the top of Knowle Road
Hedges going along to Winchester House | KCC | KCC and Farmer liaising | Farmer confirmed work will be done w/c 7/7 | Monitor
Rust on bench along Hall Road | EB | Supplier has sent a can of touch up paint.
Hedges at bungalows on Hall Lane | JM | Cut Back main hedge and cut bramble runners along Hall Road footpath | Clerk to check with Clarion to continue maintenanance | Clarion have fully cut back.
Heavy vehicles on High Street | TY | Reported to company | Said that they have to come through as there is restricted access via Borstal
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## VH
WORKING GROUPS MONTHLY ACTIONS |  |  |  | May
Part complete
WORKING GROUP: |  | VILLAGE HALL |  | Complete
LEAD |  | A. Marr, |  | Outstanding
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To plan for the ongoing development with the VH Charity, making recommendations as appropriate
Oversee and agree the terms and conditions of use of the facilities
Oversee and agree the fees relating to the hire of the facilities
Ensure that regular risk assessments and health and safety checks are made in line with current legislation
Ensure the provision of safe and well-maintained facilities for the community use.
Ensure Governing/Deed of Trust document is adhered to
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | COMPLETE/RESULT
Need to create a bin store | LC | Re-used fencing from rec | Complete | Need to remove 2 green bins to the back of the hall as not needed currently
Front garden | AMC | Group of volunteers sigened up and tidied up garden | Need to arrange regular days to maintain | Ongoing
Back garden |  | Tidied | Need to look at large funding application to make the space more usable
Closure of VH Charity | AM | Grant conditions have been sent to users | Funds have been sent. Those without bank accounts have been paid to PC to cover the cost of hall hire. | Final accounts to be submitted, then charity can be dissolved.
Annual Gas Safety Check | TM | Instructed PLT to carry out | Completed, report filed. | Complete
Bad debt | TM | Sent and received messages from user | Promised to pay half at the end of June
SUPPORT NEEDED:
RECOMMENDATIONS: |  | Suggest a 7 day letter to bad debt so that legal action can be taken
RESOLUTIONS TO FULL COUNCIL:

## H&S
WORKING GROUPS MONTHLY ACTIONS |  |  | Nov | Dec Meeting
WORKING GROUP: |  | H & S
LEAD |  | J. MILES
RESPONSIBILITIES: To meet, monitor and report on the following:
Monitor the Councils compliance with relevant legislation and progress towards best practice in health and safety including 1974 Health & Safety at Work Act
To ensure the Council’s Health and Safety Policy is implemented, monitored, developed, communicated effectively, reviewed and amended as required.
To ensure suitable and sufficient funds, people, materials and equipment are provided to meet all health and safety requirements
Ensure adequate insurance cover is provided and renewed
Ensure any accidents, ill health and 'near miss’s are recorded, investigated and reported where necessary
Ensure any safety issues raised are thoroughly investigated and, when necessary, further effective controls implemented
Ensure contractors engaged are reputable, can demonstrate a good health and safety records and are made aware of relevant local health and safety rules and procedures
To develop an emergency plan/disaster recovery plan involving other partners/officials where necessary and assigning a designated competent person in charge of the planning and control measures for situations involving imminent danger
Develop flood risk planning in conjunction with (h)
Develop, monitor and review risk assessments linking with the relevant committee.
Ensure checks of capital equipment and assets are made and any remedial actions taken
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS/NEXT STEPS | NEXT STEPS, COMPLETE/RESULT
Defibs | JM | Checked | No issues | Clerk to update Circuit
Lifebuoys | JM | Checked | No issues
Loose legs on swings and seats too low | TM | Tool for tightening bolts ordered together with adjuster bolts to raise seats | Arrange to tighten bolts and raise seat.
Connector loose on cargo net | TM | as above | Remove net once tool received
Gas Safety Certifact | TM | Instrusted PLT | Completed
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL:

## Planning
WORKING GROUPS MONTHLY ACTIONS |  |  |  | May
WORKING GROUP: |  | PLANNING
LEAD |  | E. BELL
RESPONSIBILITIES: To meet, monitor and report on the following:
To make representations to the Local Planning Authority on applications for planning permission which have been notified to the Council
To make representations in respect of appeals against the refusal of planning permission
To identify and make representations to the relevant authorities in respect of enforcement action or any matters considered to be breaches of planning regulations;
The Working Group will consider each application on its merits.
All Parish Council members are notified of applications within 3 working days of Parish meeting and may be viewed via the Tonbridge and Malling Planning Portal. All Committee decisions will be recorded in the Parish Council minutes.
The Working Group, whilst considering the views of residents and other interested parties, is not duty bound to pass on these views when making its decision, they may submit a budget to the Council as part of the Council’s overall budget process.
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/ RESULT

## F&A
WORKING GROUPS MONTHLY ACTIONS
WORKING GROUP: |  | FINANCE
LEAD |  | E. BELL
DELEGATED RESPONSIBILITIES: To meet, monitor and report on the following:
To consider the quarterly budget monitoring reports provided by the Clerk with any recommendations being put to the Council.
To consider the annual budget and the annual precept and take recommendations and comments to the full council.
All Council members will be provided with a list of payments for approval prior to each Council meeting. Any payment can be queried at the Council meetings. If necessary, a vote be taken to authorise payment with the Chairman of the Council Meeting having the casting vote when there are equal numbers of votes.
A member of the WG will sign off the bank statement from the previous month, at each Council meeting.
During each Council meeting, 2 bank signatories, will agree payments for the month.
To monitor staffing in line with the Terms of Reference
ISSUE RAISED | LEAD | ACTION TAKEN | PROGRESS | COMPLETE/RESULT
SUPPORT NEEDED:
RECOMMENDATIONS:
RESOLUTIONS TO FULL COUNCIL: